## Schedule
Crew Member | 2016-02-21 | 2016-02-28 | 2016-03-06 | 2016-03-13 | 2016-03-20 | 2016-03-27 | 2016-04-03

## OLD-TaskList
Status | Catagory | Task | Assigned To | Target Date | Notes
completed | Ads | Organize local business/senior home adverts | Joe | 2015-10-29 | Gabes Going To Southfield Pavilion
completed | Ads | Remind cast/crew to make fb posts | Joe/Jillian/Gabe | 2015-10-18
completed | Ads | Deploy to local businesses/senior homes | ALL | 2015-10-18 | Flexible albeit quite rushed
Working | Ads | Start weekly posts, energy building snippets, etc | Joe | 2015-10-18
Working | Ads | Determine on-campus hype-building methods | ALL |  | Here's really hoping...
Working | Funds | Happy Adverts | Jillian/Joe | 2015-10-06 | Link needs to go up
completed | Funds | Items List for Soda Floats | Jillian | 2015-10-24 | Get people list
Working | Funds | Call Buisness for Advertisements | All | Ongoing | Working on Availabilities
completed | Funds | Promote soda floats item donation | Tj
completed | Other | Review publication timeline for playbill printing | Joe | 2015-10-15
Working | Other | cast and crew Bios | Jillian | 2015-10-18 | about 5 people to gather
completed | Other | Get Ann on starting rehearsal photos | Joe |  | Anns going to start this weekend
Working | Other | Tee Shirts | Gabe | 2015-10-24 | Getting Counts
Working | Other | Design/edit/manage playbill content | Joe | 2015-10-18
Working | Other | Nice messages and flowers to the cast | Gabe | 2015-10-18
Working | Other | Approval for playbills | Joe/Jillian/Gabe | 2015-10-22
Working | Other | Print playbills | Joe | 2015-10-26
Working | Other | Stapling / folding playbills | Joe | 2015-11-10 | whenever works, tentative timeframe
pending | Funds | Collect Donations | Jillian
completed | Ads | Build LTU SODA FB page interest | ALL | 2015-10-24
completed | Ads | SODA Floats FB event / sharing | Joe | 2015-10-14
Completed | Ads | Production FB event | Joe | 2015-10-14
Completed | Ads | Email to campus/faculty lists (no flyer) | Joe | 2015-10-14
Completed | Ads | Dr. Scott Blurb | Joe | 2015-10-16 | Posting on Friday
Completed | Ads | Email to campus/faculty/student lists (w/ flyer) | Joe | 2015-10-16 | Posting on Friday
Completed | Ads | Print campus flyers | Joe | 2015-10-16 | Joe will print
Completed | Ads | Design social media broadcasting campaign plan | ALL | 2015-10-23
Completed | Ads | Face Book Hype Paragragh | Tj/Jillian/Emily | 2015-10-16
completed |  | Sweetest Day stuff Gathered | all | 2015-10-10 | flowers ordered, anns flowers, ask all for sweets, posters, volunteers
completed |  | First base ad | Ann | 2015-10-11
Completed |  | Plan team meeting | Gabe | 2015-10-11 | Will work out with joe today.
completed |  | Social Media Passwords For PR+Joe | Jillian | 2015-10-04
completed |  | Atrium Reservation | Jillian | 2015-10-06 | submitted waiting for response
completed |  | Flyers for Sweetest Day | Jillian | 2015-10-07
completed |  | Sweetest Day rush advertising | Joe | 2015-10-12
completed |  | Email for Bios | Jillian
completed |  | Volunteering Sheet | Jillian
completed |  | Email for Volunteers | Jillian