## Sheet1
Risk | Impact on Project | Likelyness (1 -10) | Severity (1-10) | Action Midigation | Timeline For Midigation
Injury from Set | Could delay certain tasks that person was in charge of as well as potential shut down the show if injury is on an actor and is sevear. Also the injury in itself is very bad | 2 | 4-10 | Enforce and Cover the safety parameters when working with tools. Using glow tape to mark the potentail hazards, aslo review hazards in the meeting | All safety lessons must be completed before any construction begins.
Actors Leaving before production | Will make it extremly difficult depending on the time frame of the leave. Would have to find substitues | 3 | 6-10 | Constantly talk to actors to understand their current situations with health and family. Try to predict these events and look into getting understudies | This action must begine at the very first rehearsal and go through the show
Emergancy building Maintenance | Could Delay the set construct plan and the blocking of the set | 1 | 7 | Set Construct and blocking need to be plan out and completed as soon as possible in case these issues arise | It all must be started as soon as possible.
Extra set costs | May have to reduce size of other teams budgets which would significatly impact their performance | 4 | 4 | Item out every Item for the build. All the details must be layed out | The set design needs to have a lot of time spent to calculate all of that.
Props fail | Could prevent the show from being able to continue as normal | 6 | 2 | Actors must learn to improv and learn how to handle those situations | Should begin learn how to inprove when they go off book
Stage Breaks Mid show | Could cause injury to actors and audience members also could stop the show | 1 | 8-10 | Tripple check and validate all stage constrution | This begins as soon as the stage is build
Scheduling issues | Actors could fail there interactons with one another on stage | 6 | 3 | Enforce manditory schedule update every meeting from every actor | Happens every rehearsal
Groups fall behind schedule | Could cause certain aspects of the show to go incomplete | 7 | 3 | Makes sure they we see future issues to certain task and perform the proper change requests so we know those items are not critical | Starts from day one
Actors forgeting their lines | Could prevent the show from being able to continue as normal | 8 | 1 | Once again studying improv will help prevent this | Should begin learn how to inprove when they go off book
Alergies to the makeup | Could cause use to half to purchase new make up for actor incressing the cost | 4 | 6 | We need to ask the actors about any known make alergies right away and do a small scall test on everyone | Should start as soon as the actors are picked