## Sheet1
Project Level | Sub Level 1 | Sub Level 2
1.0 | 1.1 | 1.1.1
Design affordable housing in Bloomfield coneticuit. | The Planning Process | Define the Scope in terms of Budget and Time.
1.1.2
Inspect the Landscape.
1.1.3
Explore Potential Problems and their Solutions with the Landscape
1.1.4
Compare the different buildings materials and select the ones that have the best long term benefit for the lowest possible cost.
1.1.5
Find Contractors within the budget
| 1.2 | 1.2.1
| The Physical Design Process | Design the Foundation
1.2.2
Design the Structural Support for each building
1.2.3
Design The extieror of the Buildings
1.2.4
Design the road layout
1.2.5
Design the landscape
| 1.3 | 1.3.1
| The Construction Process | Teraform the land.
1.3.2
Lay in the foundation
1.3.3
Build the structure of each building
1.3.4
Finish the External parts of each building.
1.3.5
Build and Finish the Inteirors
1.3.6
Pave the roads of around the buildings
1.37
Build the Land Scape.